## Forward Traceability
Requirements | Tests | Executions | Defects
MIHA-51 - As a user I want to be able to define Work Shifts. | MIHA-93 - Verify that a Work Shift can be added by filling required fields with valid data. | CS for Admin module - PASS | None
MIHA-51 - As a user I want to be able to define Work Shifts. - 1 defect | MIHA-94 - Verify that on Add Work Shift page all required fields are marked accordingly. | CS for Admin module - FAIL | MIHA-107 - Backlog - [Job] In the Add Work Shift page, Shift Name is not marked as required field.
MIHA-51 - As a user I want to be able to define Work Shifts. | MIHA-95 - Verify that an existing Shift Name cannot be added. | CS for Admin module - PASS | None
MIHA-51 - As a user I want to be able to define Work Shifts. | MIHA-96 - Verify if the duration of working hours per day is correctly calculated when editing the Working Hours. | CS for Admin module - PASS | None
MIHA-50 - As a user I want to be able to define Job Categories. | MIHA-88 - Verify that a Job Category can be added by filling the 'Name' textbox with valid data. | CS for Admin module - PASS | None
MIHA-50 - As a user I want to be able to define Job Categories. - 1 defect | MIHA-89 - Verify that a Job Category cannot be added by filling the 'Name' textbox with invalid data(special characters). | CS for Admin module - FAIL | MIHA-106 - Backlog - [Job] When adding a new job category, I am able to fill the name of the job category with invalid data(special characters).
MIHA-50 - As a user I want to be able to define Job Categories. | MIHA-90 - Verify that a Job Category cannot be added by leaving the 'Name' textbox empty. | CS for Admin module - PASS | None
MIHA-50 - As a user I want to be able to define Job Categories. | MIHA-91 - Verify that a Job Category can be edited. | CS for Admin module - PASS | None
MIHA-50 - As a user I want to be able to define Job Categories. | MIHA-92 - Verify that a Job Category can be deleted. | CS for Admin module - PASS | None
MIHA-49 - As a user I want to be able to define Employment Status. | MIHA-85 - Verify that an Employment Status can be added by filling the 'Name' textbox with valid data. | CS for Admin module - PASS | None
MIHA-49 - As a user I want to be able to define Employment Status. - 1 defect | MIHA-86 - Verify that an Employment Status cannot be added by filling the 'Name' textbox with invalid data(special characters). | CS for Admin module - FAIL | MIHA-105 - Backlog - [Job] When adding a new employment status, I can fill the name of the employment status with special characters.
MIHA-49 - As a user I want to be able to define Employment Status. | MIHA-87 - Verify that an Employment Status can be edited. | CS for Admin module - PASS | None
MIHA-48 - As a user I want to be able to define Pay Grades. | MIHA-76 - Verify that a Pay Grade can be added by filling all required fields with valid data. | CS for Admin module - PASS | None
MIHA-48 - As a user I want to be able to define Pay Grades. - 1 defect | MIHA-77 - Verify that a Pay Grade cannot be added by filling the 'Name' field with invalid data(numbers). | CS for Admin module - FAIL | MIHA-102 - Backlog - [Job] A Pay Grade can be added by filling the 'Name' field with invalid data(numbers).
MIHA-48 - As a user I want to be able to define Pay Grades. | MIHA-78 - Verify that a Currency can be added to a Pay Grade by not filling the 'Minimum/Maximum Salary' textbox. | CS for Admin module - PASS | None
MIHA-48 - As a user I want to be able to define Pay Grades. | MIHA-79 - Verify that a Currency cannot be added to a Pay Grade by filling the 'Minimum/Maximum Salary' textbox with invalid data(letters). | CS for Admin module - PASS | None
MIHA-48 - As a user I want to be able to define Pay Grades. - 1 defect | MIHA-80 - Verify that a Currency cannot be added to a Pay Grade when 'Maximum Salary' is smaller than 'Minimum Salary'. | CS for Admin module - FAIL | MIHA-103 - Backlog - [Job] A Currency can be added to a Pay Grade when 'Maximum Salary' is smaller (0) than 'Minimum Salary'.
MIHA-48 - As a user I want to be able to define Pay Grades. | MIHA-81 - Verify that a Pay Grade can be edited. | CS for Admin module - PASS | None
MIHA-48 - As a user I want to be able to define Pay Grades. | MIHA-82 - Verify that a Pay Grade can be deleted. | CS for Admin module - PASS | None
MIHA-48 - As a user I want to be able to define Pay Grades. - 1 defect | MIHA-83 - Verify that multiple currencies can be assigned to the same Pay Grade. | CS for Admin module - FAIL | MIHA-104 - Backlog - [Job] When adding multiple currencies to the same Pay Grade, I cannot add 'Romanian Leu' currency.
MIHA-47 - As a user I want to be able to define Job Titles. | MIHA-61 - Verify that a Job Title can be added by filling all required fields with valid data. | CS for Admin module - PASS | None
MIHA-47 - As a user I want to be able to define Job Titles. | MIHA-71 - Verify that a Job Title cannot be added by leaving required fields empty. | CS for Admin module - PASS | None
MIHA-47 - As a user I want to be able to define Job Titles. - 1 defect | MIHA-72 - Verify that a Job Title cannot be added by filling 'Job title' field with invalid data(fractions). | CS for Admin module - FAIL | MIHA-101 - Backlog - [Job] A job title can be added by filling the 'Job Title' field with invalid data(fractions).
MIHA-47 - As a user I want to be able to define Job Titles. | MIHA-73 - Verify that a Job Title can be edited. | CS for Admin module - PASS | None
MIHA-47 - As a user I want to be able to define Job Titles. | MIHA-74 - Verify that multiple Job Titles can be deleted at the same time. | CS for Admin module - PASS | None
MIHA-17 - As a user I want to be able to edit a system user. | MIHA-41 - Verify that a system user can be edited by changing its username. | CS for Admin module - PASS | None
MIHA-17 - As a user I want to be able to edit a system user. | MIHA-65 - Verify that a system user can be edited by changing its user role. | CS for Admin module - PASS | None
MIHA-17 - As a user I want to be able to edit a system user. | MIHA-66 - Verify that a system user cannot be edited by changing its employee name. | CS for Admin module - PASS | None
MIHA-17 - As a user I want to be able to edit a system user. | MIHA-67 - Verify that a system user can be edited by changing its status. | CS for Admin module - PASS | None
MIHA-17 - As a user I want to be able to edit a system user. | MIHA-68 - Verify that a system user can be edited by changing the password. | CS for Admin module - PASS | None
MIHA-16 - As a user I want to be able to reset the search for a system user. | MIHA-40 - Verify that the searched information about system users can be reset. | CS for Admin module - PASS | None
MIHA-15 - As a user I want to be able to search for a system user. | MIHA-39 - Verify that a system user can be searched by username. | CS for Admin module - PASS | None
MIHA-15 - As a user I want to be able to search for a system user. - 1 defect | MIHA-60 - Verify that a system user can be searched by status. | CS for Admin module - FAIL | MIHA-98 - Backlog - [User Management] A system user cannot be searched by disabled status.
MIHA-15 - As a user I want to be able to search for a system user. | MIHA-63 - Verify that a system user can be searched by user role. | CS for Admin module - PASS | None
MIHA-15 - As a user I want to be able to search for a system user. | MIHA-64 - Verify that a system user can be searched by employee name. | CS for Admin module - PASS | None
MIHA-15 - As a user I want to be able to search for a system user. - 1 defect | MIHA-70 - Verify that 'Records Found' search can be sorted by clicking on 'Ascending'/'Descending' arrows. | CS for Admin module - FAIL | MIHA-99 - Backlog - [User Management] 'Descending' sort button is incorrectly written.
MIHA-14 - As a user I want to be able to delete a system User. | MIHA-38 - Verify that multiple entries from the System User section can be deleted simultaneously. | CS for Admin module - PASS | None
MIHA-14 - As a user I want to be able to delete a system User. | MIHA-59 - Verify that a system user can be deleted by clicking on its checkbox. | CS for Admin module - PASS | None
MIHA-13 - As a user I want to be able to add a system user. | MIHA-37 - Verify that a system user with Admin role can be added by filling all the required fields with valid data. | CS for Admin module - PASS | None
MIHA-13 - As a user I want to be able to add a system user. | MIHA-57 - Verify that a system user cannot be added when a required field is left empty. | CS for Admin module - PASS | None
MIHA-13 - As a user I want to be able to add a system user. - 1 defect | MIHA-58 - Verify that a system user cannot be added by filling 'Username' with invalid data(special characters only). | CS for Admin module - FAIL | MIHA-97 - Backlog - [User Management] For newly created system users, username can be an invalid value(special characters).
MIHA-13 - As a user I want to be able to add a system user. - 1 defect | MIHA-62 - Verify that a system user with ESS-Employee role can be added by filling all the required fields with valid data. | CS for Admin module - FAIL | MIHA-100 - Backlog - [User Management] When adding a new system user, ESS role doesn't have 'ESS-Supervisor' and 'ESS-Employee' options.